## Sheet1
ID | Requirment | Priority | Complexity | Date added | Date completed | Status | Comments | Tests | Passing?
1 | Viewing text for reading | 5 | 2 | 2016-11-12 | 14/04/2017 | Done |  | TxS4-7,TxR2-3,TxR6-7,DER2 | Passing
2 | Texts could be heard as audio | 3 | 4 | 2016-11-12 |  | Disbanded
3 | Selected sub-texts could be heard as audio | 1 | 5 | 2016-11-12 |  | Disbanded
4 | Viewing definitions of difficult words | 5 | 2 | 2016-11-12 | 27/04/2017 | Done |  | WDS6-9,DER2 | Passing
5 | Ability to answer questions related to a text after reading it | 5 | 3 | 2016-11-12 | 14/05/2017 | Done |  | AS1-5,AS9-10,AR1,AR3,DER1,DER3 | Passing
6 | Feedback for number of words in an answer | 5 | 1 | 2016-11-12 | 2017-10-03 | Done
7 | Ability to limit the number of words in each answer | 5 | 1 | 2016-11-12 | 2017-10-03 | Done
8 | Feedback for amount of connectors in an answer | 5 | 1 | 2016-11-12 | 2017-10-03 | Done
9 | Suggestions of key sentences | 5 | 1 | 2016-11-12 | 21/04/2017 | Done
10 | Feedback for repeated words in an answer | 5 | 1 | 2016-11-12 | 2017-12-06 | Done
11 | Suggestions of alternatives for repeated words in an answer | 4 | 3 | 2016-11-12 | 2017-12-06 | Done
12 | Hyperlinks to external educational online games | 2 | 1 | 2016-11-12 |  | Disbanded
13 | Score accumulatation for external educational online games | 2 | 5 | 2016-11-12 |  | Disbanded
14 | Ability to track scores progress | 2 | 5 | 2016-11-12 |  | Disbanded
15 | Ability to track pupils tasks | 2 | 4 | 2016-11-12 |  | Disbanded
16 | Ability to compare between scores of other pupils | 1 | 3 | 2016-11-12 |  | Disbanded
17 | "Check" button - upon clicking the pupil recieves feedback for answer | 5 | 4 | 2016-11-12 | 20/01/2017 | Done
18 | Marking and correcting sequence of repeated words | 2 | 2 | 2016-11-12 |  | Disbanded
19 | New texts could be added to the system | 5 | 2 | 2016-11-12 | 14/04/2017 | Done |  | TxS1-3,TxR1,DER1 | Passing
20 | Existing texts could be edited | 3 | 2 | 2016-11-12 | 21/04/2017 | Done |  | TxS8-10,TxR3,TxR4,DER2 | Passing
21 | Existing texts could be removed from the system | 5 | 2 | 2016-11-12 | 21/04/2017 | Done |  | TxR5,TxR8,TxS11-13,DER4 | Passing
22 | New audio could be added to the system | 5 | 3 | 2016-11-12 |  | Disbanded
23 | Existing audio could be replaced | 5 | 2 | 2016-11-12 |  | Disbanded
24 | Existing audio could be removed from the system | 5 | 2 | 2016-11-12 |  | Disbanded
25 | New words definitions could be added to the system | 5 | 2 | 2016-11-12 | 27/05/2017 | Done |  | WDS1-5,DER1 | Passing
26 | Existing words definitions could be edited | 3 | 2 | 2016-11-12 |  | Disbanded |  | WDS4-5,WDS10-11 | Passing
27 | Existing words definitions could be removed | 3 | 2 | 2016-11-12 |  | Disbanded |  | WDS12-14 | Passing
28 | New questions could be added to the system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done |  | HWS11.1-15,HWR4,DER3 | Passing
29 | Existing questions could be edited | 3 | 2 | 2016-11-12 | 2017-12-06 | Partially Done |  | HWS11.2-15,HWR4,DER3 | Passing
30 | Existing questions could be removed from the system | 3 | 2 | 2016-11-12 | 2017-12-06 | Partially Done |  | HWS11.3-15,HWR4,DER3 | Passing
31 | New key sentences could be added | 5 | 2 | 2016-11-12 | 23/05/2017 | Done |  | HWS11.4,HWR3,DER3 | Passing
32 | Existing key sentences could be edited | 3 | 2 | 2016-11-12 | 2017-12-06 | Partially Done |  | HWS11.5,HWR3,DER3 | Passing
33 | Existing key sentences could be removed | 3 | 2 | 2016-11-12 | 2017-12-06 | Partially Done |  | HWS11.6,HWR3,DER3 | Passing
34 | Feedback for punctuation marks usage | 2 | 3 | 2016-11-12 |  | Disbanded
35 | Answers can be checked and feedbacked by the teacher | 5 | 3 | 2016-11-12 | 28/05/2017 | Done |  | HWS10,10.1,11,12,HWR2-4,HWR6,DER2,3 | Passing
36 | Control over font and display - size, underline, bold | 2 | 2 | 2016-11-12 | 23/05/2017 | Done
37 | New pupils users could be added to system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done |  | SS1-3,SR1,SR10-12,DER1 | Passing
38 | Existing pupils users details could be edited | 4 | 2 | 2016-11-12 | 23/05/2017 | Done |  | SS8-11,SR4,DER3 | Passing
39 | Existing pupils users could be removed from the system | 4 | 2 | 2016-11-12 | 23/05/2017 | Done |  | SS12-15,SR5,DER4 | Passing
40 | New teachers users could be added to the system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done |  | TS1-3,TR1,TR9-10,DER1 | Passing
41 | Existing teachers users details could be edited | 4 | 2 | 2016-11-12 | 23/05/2017 | Done |  | TS8-11,TR4,DER3 | Passing
42 | Existing teachers users could be deleted from the system | 4 | 2 | 2016-11-12 | 23/05/2017 | Done |  | TS12-15,SR5,DER4 | Passing
43 | Pupils could log in to the system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done
44 | Pupils could log out of the system | 4 | 1 | 2016-11-12 | 23/05/2017 | Done
45 | Teachers could log in to the system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done
46 | Teachers could log out of the system | 4 | 1 | 2016-11-12 | 23/05/2017 | Done
47 | Answer could be submitted | 5 | 3 | 2016-11-13 | 2017-06-05 | Done |  | AS1-5,AS9-10,AR1,AR3,DER1,DER3 | Passing
48 | Pupil will get a notification when he got a feedback | 4 | 2 | 2016-11-13 | 2017-06-05 | Done |  | AS10.2 | Passing
49 | Pupils can be connected to a class | 5 | 2 | 2016-11-13 | 23/05/2017 | Done |  | SCS13.2, SCS12.3, SCR4,DER3 | Passing
50 | Teachers can be connected to a class | 5 | 2 | 2016-11-13 | 23/05/2017 | Done |  | SCS13.5,SCR4,DER3 | Passing
51 | Pupils can be disconnected from a class | 4 | 2 | 2016-11-13 | 23/05/2017 | Done |  | SCS13.1,SCS12.3,SCR4,DER3 | Passing
52 | Teachers can be disconnected from a class | 4 | 2 | 2016-11-13 |  | Testing |  | SCS13.4,SCS12.3,SCR3,DER3 | Passing
53 | A class can be created | 5 | 2 | 2016-11-13 | 2017-12-06 | Done |  | SCS1-3,SCR1,DER1 | Passing
54 | Class details can be edited | 4 | 2 | 2016-11-13 | 2017-12-06 | Done |  | SCS10-13.5,SCR4,DER3 | Passing
55 | A class can be removed | 4 | 2 | 2016-11-13 | 2017-12-06 | Done |  | SCS14-19,SCR5,DER4 | Passing
56 | pupils get notification for new uploaded assignment | 3 | 3 | 2016-11-13 | 2017-12-06 | Done
57 | The list of all of the classes can be viewed | 5 | 2 | 2016-11-16 | 2017-12-06 | Done |  | SCS6-9,SCR2-3,SCR6,DER2 | Passing
58 | The list of all of the pupils in a specific class can be viewed | 5 | 2 | 2016-11-16 | 2017-12-06 | Done |  | SCS9.1,SCR3,DER2 | Passing
59 | The list of all of the teachers in a specific class can be viewed | 5 | 2 | 2016-11-16 | 2017-12-06 | Done |  | SCS9.2,SCR3,DER2 | Passing
60 | Pupil's details can be viewed by any teacher teaching him | 5 | 2 | 2016-11-29 | 28/05/2017 | Done
61 | Pupil's details can be viewed by himself | 1 | 2 | 2016-11-29 |  | Disbanded
62 | Details about a teacher can be viewed by all teachers | 1 | 2 | 2016-11-29 |  | Disbanded
63 | Details about a teacher can be viewed by their pupils | 1 | 2 | 2016-11-29 |  | Disbanded
64 | A list of all teachers in the system can be viewed | 5 | 2 | 2016-11-16 | 2017-12-06 | Done |  | TS4-7,TR3,DER2 | Passing
65 | A list of all pupils in the system can be viewed | 5 | 2 | 2016-11-16 | 28/05/2017 | Done |  | SS5-7,TR3,DER2 | Passing