## Sheet1
ID | Requirment | Priority | Complexity | Date added | Date completed | Status | Comments | Unit Tests
1 | Viewing text for reading | 5 | 2 | 2016-11-12 | 14/04/2017 | Done
2 | Texts could be heard as audio | 4 | 4 | 2016-11-12 |  | In Progress
3 | Selected sub-texts could be heard as audio | 1 | 5 | 2016-11-12 |  | In Progress
4 | Viewing definitions of difficult words | 5 | 2 | 2016-11-12 | 27/04/2017 | Done
5 | Ability to answer questions related to a text after reading it | 5 | 3 | 2016-11-12 | 14/05/2017 | Done
6 | Feedback for number of words in an answer | 5 | 1 | 2016-11-12 | 2017-10-03 | Done
7 | Ability to limit the number of words in each answer | 5 | 1 | 2016-11-12 | 2017-10-03 | Done
8 | Feedback for amount of connectors in an answer | 5 | 1 | 2016-11-12 | 2017-10-03 | Done
9 | Suggestions of key sentences | 5 | 1 | 2016-11-12 | 21/04/2017 | Done
10 | Feedback for repeated words in an answer | 5 | 1 | 2016-11-12 |  | In Progress | Connector words only
11 | Suggestions of alternatives for repeated words in an answer | 4 | 3 | 2016-11-12 |  | In Progress | Connector words only
12 | Hyperlinks to external educational online games | 4 | 1 | 2016-11-12 |  | In Progress
13 | Score accumulatation for external educational online games | 3 | 5 | 2016-11-12 |  | New
14 | Ability to track scores progress | 3 | 5 | 2016-11-12 |  | New
15 | Ability to track pupils tasks | 3 | 4 | 2016-11-12 |  | In Progress
16 | Ability to compare between scores of other pupils | 2 | 3 | 2016-11-12 |  | New
17 | "Check" button - upon clicking the pupil recieves feedback for answer | 5 | 4 | 2016-11-12 | 20/01/2017 | Done
18 | Marking and correcting sequence of repeated words | 3 | 2 | 2016-11-12 |  | In Progress
19 | New texts could be added to the system | 5 | 2 | 2016-11-12 | 14/04/2017 | Done
20 | Existing texts could be edited | 3 | 2 | 2016-11-12 | 21/04/2017 | Done
21 | Existing texts could be removed from the system | 5 | 2 | 2016-11-12 | 21/04/2017 | Done
22 | New audio could be added to the system | 5 | 3 | 2016-11-12 |  | New
23 | Existing audio could be replaced | 5 | 2 | 2016-11-12 |  | New
24 | Existing audio could be removed from the system | 5 | 2 | 2016-11-12 |  | New
25 | New words definitions could be added to the system | 5 | 2 | 2016-11-12 | 27/05/2017 | Done
26 | Existing words definitions could be edited | 5 | 2 | 2016-11-12 |  | New
27 | Existing words definitions could be removed | 5 | 2 | 2016-11-12 |  | New
28 | New questions could be added to the system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done
29 | Existing questions could be edited | 5 | 2 | 2016-11-12 |  | New
30 | Existing questions could be removed from the system | 5 | 2 | 2016-11-12 |  | New
31 | New key sentences could be added | 5 | 2 | 2016-11-12 | 23/05/2017 | Done
32 | Existing key sentences could be edited | 4 | 2 | 2016-11-12 |  | New
33 | Existing key sentences could be removed | 4 | 2 | 2016-11-12 |  | New
34 | Feedback for punctuation marks usage | 4 | 3 | 2016-11-12 |  | In Progress
35 | Answers can be checked and feedbacked by the teacher | 5 | 3 | 2016-11-12 | 28/05/2017 | Done
36 | Control over font and display - size, color, underline, bold | 2 | 2 | 2016-11-12 | 23/05/2017 | Done | no color
37 | New pupils users could be added to system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done
38 | Existing pupils users details could be edited | 4 | 2 | 2016-11-12 | 23/05/2017 | Done
39 | Existing pupils users could be removed from the system | 4 | 2 | 2016-11-12 | 23/05/2017 | Done
40 | New teachers users could be added to the system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done
41 | Existing teachers users details could be edited | 4 | 2 | 2016-11-12 | 23/05/2017 | Done
42 | Existing teachers users could be deleted from the system | 4 | 2 | 2016-11-12 | 23/05/2017 | Done
43 | Pupils could log in to the system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done
44 | Pupils could log out of the system | 4 | 1 | 2016-11-12 | 23/05/2017 | Done
45 | Teachers could log in to the system | 5 | 2 | 2016-11-12 | 23/05/2017 | Done
46 | Teachers could log out of the system | 4 | 1 | 2016-11-12 | 23/05/2017 | Done
47 | Answer could be submited | 5 | 3 | 2016-11-13 |  | In Progress | UI only
48 | Pupil will get a notification when he got a feedback | 4 | 2 | 2016-11-13 |  | In Progress
49 | Pupils can be connected to a class | 5 | 2 | 2016-11-13 | 23/05/2017 | Done
50 | Teachers can be connected to a class | 5 | 2 | 2016-11-13 | 23/05/2017 | Done
51 | Pupils can be disconnected from a class | 4 | 2 | 2016-11-13 | 23/05/2017 | Done
52 | Teachers can be disconnected from a class | 4 | 2 | 2016-11-13 |  | Testing
53 | A class can be created | 5 | 2 | 2016-11-13 |  | Testing
54 | Class details can be edited | 4 | 2 | 2016-11-13 |  | Testing
55 | A class can be removed | 4 | 2 | 2016-11-13 |  | Testing
56 | pupils get notification for new uploaded assignment | 3 | 3 | 2016-11-13 |  | In Progress
57 | The list of all of the classes can be viewed | 5 | 2 | 2016-11-16 |  | Testing
58 | The list of all of the pupils in a specific class can be viewed | 5 | 2 | 2016-11-16 |  | Testing
59 | The list of all of the teachers in a specific class can be viewed | 5 | 2 | 2016-11-16 |  | Testing
60 | Pupil's details can be viewed by any teacher teaching him | 5 | 2 | 2016-11-29 | 28/05/2017 | Done
61 | Pupil's details can be viewed by himself | 5 | 2 | 2016-11-29 |  | In Progress
62 | Details about a teacher can be viewed by all teachers | 5 | 2 | 2016-11-29 |  | In Progress
63 | Details about a teacher can be viewed by their pupils | 5 | 2 | 2016-11-29 |  | In Progress
64 | A list of al teachers in the system can be viewed | 5 | 2 | 2016-11-16 |  | In Progress
65 | A list of all pupils in the system can be viewed | 5 | 2 | 2016-11-16 | 28/05/2017 | Done